## Dashboard
BMS Project Plan Dashboard
Banquet Date | 2014-09-15
Goal Tracking | Goal | Actual | Percentage
Number of Applications Received |  |  | #DIV/0!
Total Number of Banquet Attendees |  |  | #DIV/0!
Chapter Attendance at Banquet (%) |  |  | #DIV/0!
Number of Finalists who Received Bids |  |  | #DIV/0!
Number of Finalists who Accepted Bids |  |  | #DIV/0!
Number of Non-finalist Applicants who Received Bids |  |  | #DIV/0!
Number of Non-Finalist Applicants who Accepted Bids |  |  | #DIV/0!
Total Number of Applicants Recruited |  |  | #DIV/0!
Number of Scholarships Awarded |  |  | #DIV/0!
Total Value of Scholarships Awarded |  |  | #DIV/0!

## BMS Assessment
Balanced Man Scholarship Assessment
GOALS | 2012-13 | 2013-14 | 2014-15 | 2015-16
Application Goal
Actual/Goal | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
BMS Recruitment Goal
Actual/Goal | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
DATA | 2012-13 | 2013-14 | 2014-15 | 2015-16
Term Awarded (Fall, Winter, Spring)
Date Applications Mailed
Date Applications Emailed
Number of Applications Received
Application Due Date
Number of Phone Interviews Completed
Number of In-Person Interviews Completed (not counting in-home)
Number of In-Home Interviews Completed
Number of Finalist Interviews Completed
Awards Banquet or Reception Date
Total Number of Banquet Attendees
Chapter Attendance at Banquet (%)
Number of Finalists who Received Bids
Number of Finalists who Accepted Bids
Number of Non-finalist Applicants who Received Bids
Number of Non-Finalist Applicants who Accepted Bids
Total Number of Applicants Recruited
Number of Scholarships Awarded
Total Value of Scholarships Awarded
BEST PRACTICES (Y/N) | 2012-13 | 2013-14 | 2014-15 | 2015-16
Stage 1: Prepare
Was a BMS chairman appointed that was not the VP of recruitment?
Did the chairman establish a timeline with dates and deadlines?
Did the chairman create a detailed budget for the scholarship with the VP finance?
Was a BMS committee selected?
Did an alumni volunteer serve as a mentor for the BMS committee?
Did the chairman secure a mailing list for incoming freshmen?
Did the chairman secure an email list for incoming freshmen?
Did the chairman secure a mailing list for feeder high schools?
Were application materials prepared 6-8 months in advance?
Was there a cover letter outlining why the scholarship is being offered?
Was an online application available?
Is the application simple and easy to complete, without an essay?
Did the application list eligibility requirements?
Was the scholarship available only to men?
Was the banquet venue reserved 6-8 months in advance?
Did the chairman put the banquet on the chapter calendar?
Was a keynote speaker secured 6-8 months in advance?
Were invitations sent to guests 5-6 months in advance?
Did the chairman recruit and train interviewers?
Stage 2: Market Application
Was a hardcopy mailing to incoming freshmen men completed?
Was a hardcopy mailing to high school counselors completed?
Was the application emailed to all incoming freshmen men?
Was the scholarship advertised online?
Was the scholarship advertised via social media?
Was the scholarship advertised on campus?
Did the committee call high school counselors to follow-up on applications?
Were deadline reminders sent to incoming freshmen and high school counselors?
Did the committee organize application information in a spreadsheet?
Did the committee rank applicants?
Did the committee notify applicants that their application was received?
Stage 3: Interview Applicants
Did the committee remove and notify any ineligible applicants?
Did the chairman create an interview plan?
Were applicants divided between interviewers?
Did interviewers conduct 30 minute in-person first round interviews?
Was every applicant who was eligible for membership interviewed?
Did interviewers dress in at least business casual attire?
Did interviewers successfully spark interest in SigEp?
Did interviewers submit interview evaluations?
Did the committee select and notify finalists?
Were invitations to the awards banquet sent to finalists and their parents?
Were finalist bios sent to the chapter?
Did the committee notify non-finalists?
Were finalists interviewed by a 2-3 man committee?
Did the committee select scholarship winners with alumni volunteer assistance?
Stage 4: Recognize Applicants
Did the chapter host a BMS awards banquet or reception?
Was the banquet hosted 2-14 days before the beginning of formal recruitment?
Was the banquet held at a professional banquet hall (on or off campus)?
Was a plated or family style meal served at the banquet?
Was the banquet substance-free?
Did the chapter give awards/scholarships to members at the banquet?
Were award certificates presented to finalists and award winners?
Did the committee create seating assignments?
Did the chairman develop a banquet script 2-4 weeks in advance?
Did speakers rehearse the script 2-4 weeks in advance?
Were non-recipients given consolation prizes?
Were parents in attendance?
Were Fraternity/Sorority Life or Student Affairs staff members in attendance?
Were alumni volunteers in attendance?
Were faculty members in attendance?
Did the committee send hand-written thank you notes to guests?
Stage 5: Recruit Applicants
Did the recruitment committee add all qualified applicants to the PNML?
Did the chapter provide opportunities to help applicants acclimate to campus?
Did the committee invite applicants to chapter events?
Did the chapter help applicants move into their dorms?
Did committee/chapter members meet with applicants informally?
Did the chapter provide opportunities for applicants to learn more about SigEp?
Did the committee call applicants to invite them to recruitment events?
Did the chapter meet/exceed its BMS recruitment goal?
Did the chapter meet/exceed its recruitment goal for the term?

## BMS Budget
Balanced Man Scholarship Budget
|  | Previous Year |  | Current Year
REVENUES |  | Budget | Actual | Budget | Actual
Chapter Contribution
Fundraising
Chapter Scholarship Fund
AVC Contribution
Parents' Club Contribution
Alumni Donations
Banquet Tickets
Alumni
Undergraduate Members
| TOTAL REVENUE | 0 | 0 | 0 | 0
|  | Previous Year |  | Current Year
EXPENSES |  | Budget | Actual | Budget | Actual
Scholarships
First Place
Second Place
Third Place
Printing
Cover Letters
Applications
Flyers
Banquet Invitations
Banquet Programs
Banquet Place Cards
Certificates/Plaques
Thank-you Notes
Marketing
Envelopes
Postage/Mailing
Interviews
Travel Expenses (in-home)
Meeting Room Rental
Awards Banquet
Room Rental
A/V Equipment
Decorations
Food
Meals
Refreshments
Dessert
Miscellaneous
Consolation Prizes
TOTAL EXPENSES
NET

## Project Plan
Balanced Man Scholarship Project Plan
Stage | Task | Timeframe | Deadline | Notes | Status
1 - Prepare | Select a BMS Chairman | 8-10 months before banquet | (Choose a Date) | The BMS Chairman should be a member who is organized, responsible, and who delegates responsibility well. The BMS chairman should not be the VP of Recruitment.
1 - Prepare | Complete BMS assessment for previous year | 8-10 months before banquet | (Choose a Date) | Work with the previous BMS chairman, alumni mentor, chapter counselor, and/or your regional director to complete the BMS assessment for the previous year.
1 - Prepare | Select a BMS committee | 8-10 months before banquet | (Choose a Date) | Appoint a committee to assist the chairman. The committee should include old and young members and at least one volunteer.
1 - Prepare | Establish a time line for the scholarship | 8-10 months before banquet | (Choose a Date) | Use this document to create a comprehensive timeline for running the scholarship including a scholarship deadline and banquet date.
1 - Prepare | Establish a budget for the scholarship | 8-10 months before banquet | (Choose a Date) | Work with the VP of Finance and the AVC Treasurer to create a budget for the scholarship.
1 - Prepare | Build BMS application | 6-8 months before banquet | (Choose a Date) | Edit application to reflect college/university and ensure it is simple, concise, and easy to complete.
1 - Prepare | Write cover letter for potential applicants | 6-8 months before banquet | (Choose a Date) | Focus on explaining the scholarship, not SigEp. Direct applicants to online application.
1 - Prepare | Write cover letter for high school counselors | 6-8 months before banquet | (Choose a Date) | Explain the scholarship and ask that the counselor distribute the BMS application to men planning on attending your college/university
1 - Prepare | Meet with Greek life professional | 6-8 months before banquet | (Choose a Date) | Schedule a meeting with the Greek life professional on your campus to discuss your scholarship plan and ask for advice or suggestions.
1 - Prepare | Secure mailing/emailing lists for incoming freshmen | 6-8 months before banquet | (Choose a Date) | Work with college/university staff (Greek life, registrar, financial aid, admissions, etc.) to obtain a list of the name, mailing address, and email address of every male incoming freshman with above a 3.0 high school GPA. If they cannot release this information to you, ask if you can provide stamped and prepared envelopes for them to address or if they can send an email on your behalf.
1 - Prepare | Secure high school counseling office mailing list | 6-8 months before banquet | (Choose a Date) | Work with college/university staff to obtain a list of the top 100 feeder schools for your institution and their mailing addresses.
1 - Prepare | Establish website application with a form that links to a spreadsheet | 6-8 months before banquet | (Choose a Date) | Use a Google form to imbed the application on your chapters website. Be sure to include the link in your application materials.
1 - Prepare | Recruit and secure a keynote speaker | 6-8 months before banquet | (Choose a Date) | Make a list of potential keynote speakers and check their availability to speak at your banquet.
1 - Prepare | Find and reserve an award banquet venue | 6-8 months before banquet | (Choose a Date) | Find a presentable venue to host the awards banquet. Many campuses have banquet rooms available on campus.
1 - Prepare | Select and train interviewers | 5-6 months before banquet | (Choose a Date) | Identify a dependable group of members to interview scholarship applicants. Work with volunteers and your regional director to train interviewers.
1 - Prepare | Notify the chapter of banquet date/time | 5-6 months before banquet | (Choose a Date) | Inform chapter members of the date, time, location, attire, and cost of the awards banquet. Be sure to set an RSVP deadline.
1 - Prepare | Send banquet invitations | 5-6 months before banquet | (Choose a Date) | Send invitations to college/university staff, faculty, alumni volunteers, Greek life staff, and parents well in advance.
2 - Market Application | Complete hardcopy mailing to incoming freshmen | 5-6 months before banquet | (Choose a Date) | Send a hardcopy of your cover letter and application to each incoming freshman.
2 - Market Application | Complete hardcopy mailing to high school counselors | 5-6 months before banquet | (Choose a Date) | Send a hardcopy of your cover letter for high school counselors along with several cover letters and applications.
2 - Market Application | Email scholarship information to incoming freshmen |  | (Choose a Date) | Send an email version of your cover letter and link to online application to all incoming freshmen men.
2 - Market Application | Advertise scholarship online | 5-6 months before banquet | (Choose a Date) | Post scholarship on chapter, financial aid, fraternity and sorority life, admissions and scholarship search websites.
2 - Market Application | Advertise scholarship on campus (optional) | 3-5 months before banquet | (Choose a Date) | Post flyers around campus advertising the scholarship (Spring BMS)
2 - Market Application | Call high school counselors to follow up | 3-5 months before banquet | (Choose a Date) | Call each high school counselor to make sure they received your materials and have shared them with their students.
2 - Market Application | Drive applications with follow-up emails | 3-5 months before banquet | (Choose a Date) | Remove those who have already applied and send reminder emails one month and one week prior to the deadline
2 - Market Application | Rank applicants | 3-5 months before banquet | (Choose a Date) | Identify priority candidates based on sound mind, sound body, academics, leadership, and service. Make sure priority candidates go to your best interviewers.
2 - Market Application | Notify applicants that their application has been received | 3-5 months before banquet | (Choose a Date) | Call each applicant to notify them that their application has been received and ask if they have any questions.
3 - Interview Applicants | Eliminate ineligible applicants | 3-5 months before banquet | (Choose a Date) | Eliminate any applicants that do not qualify to be considered for membership in SigEp, including women and applicants who will not be attending your college/university.
3 - Interview Applicants | Notify ineligible applicants | 3-5 months before banquet | (Choose a Date) | Email ineligible applicants, thank them for their application, and politely notify them that they have not been selected.
3 - Interview Applicants | Create an interview plan | 3-5 months before banquet | (Choose a Date) | Create a plan to guide the efforts of your interviews that includes when and where interviews will be conducted.
3 - Interview Applicants | Assign applicants to interviewers | 3-5 months before banquet | (Choose a Date) | Divide the applicants amongst the interviewers and provide a deadline for completing interviews.
3 - Interview Applicants | Schedule interviews | 3-5 months before banquet | (Choose a Date) | Have interviewers call their applicants, congratulate them on making it to the interview round, and schedule the interview.
3 - Interview Applicants | Conduct first round interviews | 2-3 months before banquet | (Choose a Date) | (see interview guide)
3 - Interview Applicants | Follow up with interviewers | 2-3 months before banquet | (Choose a Date) | Mid-way to the interview deadline, follow-up with the interviewers to make sure they are on track to complete their interviews.
3 - Interview Applicants | Collect interview evaluations and finalist recommendations | 2-3 months before banquet | (Choose a Date) | Have interviewers complete interview evaluations after each interview and submit them prior to the interview deadline.
3 - Interview Applicants | Select and notify finalists | 6-8 weeks before banquet | (Choose a Date) | Review the evaluations and recommendations of the interviewers. Choose 15 - 20 finalists with the selection committee.
3 - Interview Applicants | Notify non-finalists | 6-8 weeks before banquet | (Choose a Date) | Email applicants not selected as finalists. Thank them for applying and remind them about upcoming events for applicants.
3 - Interview Applicants | Request transcripts from finalists | 6-8 weeks before banquet | (Choose a Date) | Have finalists submit official or unofficial high school transcripts to verify the information on their application.
3 - Interview Applicants | Arrange finalist interviews | 4-6 weeks before banquet | (Choose a Date) | Schedule interviews with finalists in an on-campus meeting room. Include the BMS chairman and one or two other members of the selection committee in the interview.
3 - Interview Applicants | Send banquet invitations to finalists and their parents | 4-6 weeks before banquet | (Choose a Date)
3 - Interview Applicants | Create finalist bios, distribute to chapter | 4-6 weeks before banquet | (Choose a Date) | Bios will also be used in the banquet script
3 - Interview Applicants | Conduct finalist interviews | 2-4 weeks before banquet | (Choose a Date) | (see interview instructions)
3 - Interview Applicants | Select scholarship winners | 2-4 weeks before banquet | (Choose a Date)
4 - Recognize Applicants | Follow up on outstanding RSVPs | 2-4 weeks before banquet | (Choose a Date) | Call guests who have not yet responded to their invitation to get a final head count.
4 - Recognize Applicants | Confirm details with venue | 2-4 weeks before banquet | (Choose a Date) | Confirm head count, room setup, start and end times, menu, parking, etc. with venue.
4 - Recognize Applicants | Confirm details with keynote speaker | 2-4 weeks before banquet | (Choose a Date) | Confirm the time, location, and parking details with the keynote speaker.
4 - Recognize Applicants | Decide on awards for chapter members | 2-4 weeks before banquet | (Choose a Date) | Choose members to receive awards and/or scholarships at the banquet (ex. Outstanding sophomore).
4 - Recognize Applicants | Order award certificates | 2-4 weeks before banquet | (Choose a Date) | Order (or make) framed certificates for scholarship and chapter member award recipients.
4 - Recognize Applicants | Determine seating arrangement | 2-4 weeks before banquet | (Choose a Date) | Use information about finalists and their parents to strategically place them at tables with members, alumni, and faculty who share their interests.
4 - Recognize Applicants | Develop awards banquet script | 2-4 weeks before banquet | (Choose a Date) | Use the sample awards banquet script to carefully plan the remarks made by chapter members and alumni at the event.
4 - Recognize Applicants | Practice awards banquet script | 2-4 weeks before banquet
4 - Recognize Applicants | Develop and print awards banquet programs | 2-4 weeks before banquet | (Choose a Date) | (see awards banquet instructions)
4 - Recognize Applicants | Prepare decorations for banquet | 2-4 weeks before banquet | (Choose a Date) | Prepare SigEp-related decorations (flag, trophies, etc.) for the banquet.
4 - Recognize Applicants | Buy consolation prizes | 2-4 weeks before banquet | (Choose a Date) | Buy consolation prizes (ex. gift cards) for finalists not receiving scholarships.
4 - Recognize Applicants | BMS Awards Banquet | 2-14 days before recruitment | 2014-09-15 | (see awards banquet instructions)
5 - Recruit Applicants | Provide opportunities to help applicants acclimate to campus | Throughout stages 2-5 |  | Offer to help applicants find their way around classes and the off campus area, introduce them to members and alumni volunteers who have the same major or career interest.
5 - Recruit Applicants | Invite applicants to chapter events | Throughout stages 2-5 |  | Invite applicants to development, athletic, philanthropy, sound mind, sound body, or informal events. Avoid recruiting with social events.
5 - Recruit Applicants | Help applicants move into their dorms (Fall BMS) | Throughout stages 2-5 |  | If allowed by your university, offer to meet applicants on move-in day and help them move into their dorm.
5 - Recruit Applicants | Meet with applicants informally | Throughout stages 2-5 |  | Spend time with applicants outside of events and interviews to become their friend.
5 - Recruit Applicants | Provide opportunities for applicants to learn more about SigEp | Throughout stages 2-5 |  | Meet with individuals or host information sessions for applicants to learn more about SigEp, the membership selection process, and the obligations of membership.
5 - Recruit Applicants | Add applicants to the potential new member list (PNML) | Throughout stages 2-5
5 - Recruit Applicants | Call applicants to invite them to recruitment events | Throughout stages 2-5

## TimeframesHide (hidden)
Banquet Date |  | 2014-09-15
EighttoTenMos |  | SixtoEightmos |  | FivetoSixMos |  | ThreetoFiveMos |  | TwotoThreeMos |  | SixtoEightWks |  | FourtoSixWks |  | TwotoFourWks |  | TaskStatus
2013-11-19 | 1900-10-26 | 2014-01-18 | 1900-08-27 | 2014-03-19 | 1900-06-28 | 2014-04-18 | 1900-05-29 | 2014-06-17 | 1900-03-30 | 2014-07-21 | 1900-02-24 | 2014-08-04 | 1900-02-10 | 2014-08-18 | 1900-01-27 | 00 - Past Due
2013-11-20 | 1900-10-25 | 2014-01-19 | 1900-08-26 | 2014-03-20 | 1900-06-27 | 2014-04-19 | 1900-05-28 | 2014-06-18 | 1900-03-29 | 2014-07-22 | 1900-02-23 | 2014-08-05 | 1900-02-09 | 2014-08-19 | 1900-01-26 | 01 - Incomplete
2013-11-21 | 1900-10-24 | 2014-01-20 | 1900-08-25 | 2014-03-21 | 1900-06-26 | 2014-04-20 | 1900-05-27 | 2014-06-19 | 1900-03-28 | 2014-07-23 | 1900-02-22 | 2014-08-06 | 1900-02-08 | 2014-08-20 | 1900-01-25 | 02 - In Progress
2013-11-22 | 1900-10-23 | 2014-01-21 | 1900-08-24 | 2014-03-22 | 1900-06-25 | 2014-04-21 | 1900-05-26 | 2014-06-20 | 1900-03-27 | 2014-07-24 | 1900-02-21 | 2014-08-07 | 1900-02-07 | 2014-08-21 | 1900-01-24 | 03 - Complete
2013-11-23 | 1900-10-22 | 2014-01-22 | 1900-08-23 | 2014-03-23 | 1900-06-24 | 2014-04-22 | 1900-05-25 | 2014-06-21 | 1900-03-26 | 2014-07-25 | 1900-02-20 | 2014-08-08 | 1900-02-06 | 2014-08-22 | 1900-01-23
2013-11-24 | 1900-10-21 | 2014-01-23 | 1900-08-22 | 2014-03-24 | 1900-06-23 | 2014-04-23 | 1900-05-24 | 2014-06-22 | 1900-03-25 | 2014-07-26 | 1900-02-19 | 2014-08-09 | 1900-02-05 | 2014-08-23 | 1900-01-22
2013-11-25 | 1900-10-20 | 2014-01-24 | 1900-08-21 | 2014-03-25 | 1900-06-22 | 2014-04-24 | 1900-05-23 | 2014-06-23 | 1900-03-24 | 2014-07-27 | 1900-02-18 | 2014-08-10 | 1900-02-04 | 2014-08-24 | 1900-01-21
2013-11-26 | 1900-10-19 | 2014-01-25 | 1900-08-20 | 2014-03-26 | 1900-06-21 | 2014-04-25 | 1900-05-22 | 2014-06-24 | 1900-03-23 | 2014-07-28 | 1900-02-17 | 2014-08-11 | 1900-02-03 | 2014-08-25 | 1900-01-20
2013-11-27 | 1900-10-18 | 2014-01-26 | 1900-08-19 | 2014-03-27 | 1900-06-20 | 2014-04-26 | 1900-05-21 | 2014-06-25 | 1900-03-22 | 2014-07-29 | 1900-02-16 | 2014-08-12 | 1900-02-02 | 2014-08-26 | 1900-01-19
2013-11-28 | 1900-10-17 | 2014-01-27 | 1900-08-18 | 2014-03-28 | 1900-06-19 | 2014-04-27 | 1900-05-20 | 2014-06-26 | 1900-03-21 | 2014-07-30 | 1900-02-15 | 2014-08-13 | 1900-02-01 | 2014-08-27 | 1900-01-18
2013-11-29 | 1900-10-16 | 2014-01-28 | 1900-08-17 | 2014-03-29 | 1900-06-18 | 2014-04-28 | 1900-05-19 | 2014-06-27 | 1900-03-20 | 2014-07-31 | 1900-02-14 | 2014-08-14 | 1900-01-31 | 2014-08-28 | 1900-01-17
2013-11-30 | 1900-10-15 | 2014-01-29 | 1900-08-16 | 2014-03-30 | 1900-06-17 | 2014-04-29 | 1900-05-18 | 2014-06-28 | 1900-03-19 | 2014-08-01 | 1900-02-13 | 2014-08-15 | 1900-01-30 | 2014-08-29 | 1900-01-16
2013-12-01 | 1900-10-14 | 2014-01-30 | 1900-08-15 | 2014-03-31 | 1900-06-16 | 2014-04-30 | 1900-05-17 | 2014-06-29 | 1900-03-18 | 2014-08-02 | 1900-02-12 | 2014-08-16 | 1900-01-29 | 2014-08-30 | 1900-01-15
2013-12-02 | 1900-10-13 | 2014-01-31 | 1900-08-14 | 2014-04-01 | 1900-06-15 | 2014-05-01 | 1900-05-16 | 2014-06-30 | 1900-03-17 | 2014-08-03 | 1900-02-11 | 2014-08-17 | 1900-01-28 | 2014-08-31 | 1900-01-14
2013-12-03 | 1900-10-12 | 2014-02-01 | 1900-08-13 | 2014-04-02 | 1900-06-14 | 2014-05-02 | 1900-05-15 | 2014-07-01 | 1900-03-16 | 2014-08-04 | 1900-02-10 | 2014-08-18 | 1900-01-27 | 2014-09-01 | 1900-01-13
2013-12-04 | 1900-10-11 | 2014-02-02 | 1900-08-12 | 2014-04-03 | 1900-06-13 | 2014-05-03 | 1900-05-14 | 2014-07-02 | 1900-03-15
2013-12-05 | 1900-10-10 | 2014-02-03 | 1900-08-11 | 2014-04-04 | 1900-06-12 | 2014-05-04 | 1900-05-13 | 2014-07-03 | 1900-03-14
2013-12-06 | 1900-10-09 | 2014-02-04 | 1900-08-10 | 2014-04-05 | 1900-06-11 | 2014-05-05 | 1900-05-12 | 2014-07-04 | 1900-03-13
2013-12-07 | 1900-10-08 | 2014-02-05 | 1900-08-09 | 2014-04-06 | 1900-06-10 | 2014-05-06 | 1900-05-11 | 2014-07-05 | 1900-03-12
2013-12-08 | 1900-10-07 | 2014-02-06 | 1900-08-08 | 2014-04-07 | 1900-06-09 | 2014-05-07 | 1900-05-10 | 2014-07-06 | 1900-03-11
2013-12-09 | 1900-10-06 | 2014-02-07 | 1900-08-07 | 2014-04-08 | 1900-06-08 | 2014-05-08 | 1900-05-09 | 2014-07-07 | 1900-03-10
2013-12-10 | 1900-10-05 | 2014-02-08 | 1900-08-06 | 2014-04-09 | 1900-06-07 | 2014-05-09 | 1900-05-08 | 2014-07-08 | 1900-03-09
2013-12-11 | 1900-10-04 | 2014-02-09 | 1900-08-05 | 2014-04-10 | 1900-06-06 | 2014-05-10 | 1900-05-07 | 2014-07-09 | 1900-03-08
2013-12-12 | 1900-10-03 | 2014-02-10 | 1900-08-04 | 2014-04-11 | 1900-06-05 | 2014-05-11 | 1900-05-06 | 2014-07-10 | 1900-03-07
2013-12-13 | 1900-10-02 | 2014-02-11 | 1900-08-03 | 2014-04-12 | 1900-06-04 | 2014-05-12 | 1900-05-05 | 2014-07-11 | 1900-03-06
2013-12-14 | 1900-10-01 | 2014-02-12 | 1900-08-02 | 2014-04-13 | 1900-06-03 | 2014-05-13 | 1900-05-04 | 2014-07-12 | 1900-03-05
2013-12-15 | 1900-09-30 | 2014-02-13 | 1900-08-01 | 2014-04-14 | 1900-06-02 | 2014-05-14 | 1900-05-03 | 2014-07-13 | 1900-03-04
2013-12-16 | 1900-09-29 | 2014-02-14 | 1900-07-31 | 2014-04-15 | 1900-06-01 | 2014-05-15 | 1900-05-02 | 2014-07-14 | 1900-03-03
2013-12-17 | 1900-09-28 | 2014-02-15 | 1900-07-30 | 2014-04-16 | 1900-05-31 | 2014-05-16 | 1900-05-01 | 2014-07-15 | 1900-03-02
2013-12-18 | 1900-09-27 | 2014-02-16 | 1900-07-29 | 2014-04-17 | 1900-05-30 | 2014-05-17 | 1900-04-30 | 2014-07-16 | 1900-03-01
2013-12-19 | 1900-09-26 | 2014-02-17 | 1900-07-28 | 2014-04-18 | 1900-05-29 | 2014-05-18 | 1900-04-29 | 2014-07-17 | 1900-02-28
2013-12-20 | 1900-09-25 | 2014-02-18 | 1900-07-27 |  |  | 2014-05-19 | 1900-04-28
2013-12-21 | 1900-09-24 | 2014-02-19 | 1900-07-26 |  |  | 2014-05-20 | 1900-04-27
2013-12-22 | 1900-09-23 | 2014-02-20 | 1900-07-25 |  |  | 2014-05-21 | 1900-04-26
2013-12-23 | 1900-09-22 | 2014-02-21 | 1900-07-24 |  |  | 2014-05-22 | 1900-04-25
2013-12-24 | 1900-09-21 | 2014-02-22 | 1900-07-23 |  |  | 2014-05-23 | 1900-04-24
2013-12-25 | 1900-09-20 | 2014-02-23 | 1900-07-22 |  |  | 2014-05-24 | 1900-04-23
2013-12-26 | 1900-09-19 | 2014-02-24 | 1900-07-21 |  |  | 2014-05-25 | 1900-04-22
2013-12-27 | 1900-09-18 | 2014-02-25 | 1900-07-20 |  |  | 2014-05-26 | 1900-04-21
2013-12-28 | 1900-09-17 | 2014-02-26 | 1900-07-19 |  |  | 2014-05-27 | 1900-04-20
2013-12-29 | 1900-09-16 | 2014-02-27 | 1900-07-18 |  |  | 2014-05-28 | 1900-04-19
2013-12-30 | 1900-09-15 | 2014-02-28 | 1900-07-17 |  |  | 2014-05-29 | 1900-04-18
2013-12-31 | 1900-09-14 | 2014-03-01 | 1900-07-16 |  |  | 2014-05-30 | 1900-04-17
2014-01-01 | 1900-09-13 | 2014-03-02 | 1900-07-15 |  |  | 2014-05-31 | 1900-04-16
2014-01-02 | 1900-09-12 | 2014-03-03 | 1900-07-14 |  |  | 2014-06-01 | 1900-04-15
2014-01-03 | 1900-09-11 | 2014-03-04 | 1900-07-13 |  |  | 2014-06-02 | 1900-04-14
2014-01-04 | 1900-09-10 | 2014-03-05 | 1900-07-12 |  |  | 2014-06-03 | 1900-04-13
2014-01-05 | 1900-09-09 | 2014-03-06 | 1900-07-11 |  |  | 2014-06-04 | 1900-04-12
2014-01-06 | 1900-09-08 | 2014-03-07 | 1900-07-10 |  |  | 2014-06-05 | 1900-04-11
2014-01-07 | 1900-09-07 | 2014-03-08 | 1900-07-09 |  |  | 2014-06-06 | 1900-04-10
2014-01-08 | 1900-09-06 | 2014-03-09 | 1900-07-08 |  |  | 2014-06-07 | 1900-04-09
2014-01-09 | 1900-09-05 | 2014-03-10 | 1900-07-07 |  |  | 2014-06-08 | 1900-04-08
2014-01-10 | 1900-09-04 | 2014-03-11 | 1900-07-06 |  |  | 2014-06-09 | 1900-04-07
2014-01-11 | 1900-09-03 | 2014-03-12 | 1900-07-05 |  |  | 2014-06-10 | 1900-04-06
2014-01-12 | 1900-09-02 | 2014-03-13 | 1900-07-04 |  |  | 2014-06-11 | 1900-04-05
2014-01-13 | 1900-09-01 | 2014-03-14 | 1900-07-03 |  |  | 2014-06-12 | 1900-04-04
2014-01-14 | 1900-08-31 | 2014-03-15 | 1900-07-02 |  |  | 2014-06-13 | 1900-04-03
2014-01-15 | 1900-08-30 | 2014-03-16 | 1900-07-01 |  |  | 2014-06-14 | 1900-04-02
2014-01-16 | 1900-08-29 | 2014-03-17 | 1900-06-30 |  |  | 2014-06-15 | 1900-04-01
2014-01-17 | 1900-08-28 | 2014-03-18 | 1900-06-29 |  |  | 2014-06-16 | 1900-03-31
2014-01-18 | 1900-08-27 | 2014-03-19 | 1900-06-28 |  |  | 2014-06-17 | 1900-03-30